## Ryan
Date | Time Start | Time End | Total Time | Description
2023-06-13 | 13:00 | 16:30 | 3.5 h | Met with group and collaborated on research related to python libraries we could use for the project and possible APIs
2023-06-14 | 13:00 | 16:00 | 3 h | Conducted API Research. Discovered Open-Meteo, and wrote python code to test pulling. This code was shared with the group.
2023-06-17 | 19:00 | 22:30 | 3.5 h | Conducted extensive testing on the speed of the found API.
2023-06-19 | 13:00 | 15:00 | 2 h | Conducted research on tileservers
2023-06-21 | 13:30 | 5:30:PM | 4 h | Conducted more research on tileservers and wrote python code to pull a tile from a server based on coordinates. This code is pushed on a separate branch.
2023-06-22 | 12:30 | 16:30 | 4 h | Reviewed current code and fixed date error in which end date could precede current date by linking a new update function. This code was pushed.
2023-06-25 | 7:30 | 14:00 | 6.5 h | Wrote rust function to call api and return resulting json to python. This function went through many variations, all code was pushed.
2023-06-26 | 6:30 | 8:30 | 2 h | Found a way to display an image on top of the folium map through an icon. This code was pushed.
2023-06-26 | 12:00 | 0:00 | 12 h | Worked with team to finish project for submission. Wrote code from python end to call geocoords rust function. Helped debug import errors. All code was pushed.
2023-06-27 | 13:00 | 22:30 | 9.5 h | Worked with team to finish project for later submission. Worked on moving api calls to a separate thread, wrote functionality for the date slider, and fixed various bugs. All code was pushed.
2023-07-11 | 10:00 | 15:00 | 5 h | Met with Carsten about the state of our project. Started researching new APIs due to the poor performance of our prototype API
2023-07-11 | 19:00 | 0:00 | 5 h | Discovered through benchmarking that api might not be the issue. Began to work on alternative ways of speeding up query performance
2023-07-12 | 14:00 | 19:00 | 5 h | Switched API calling to python with parallel calls. Also made it so progress bar is correctly signaled and updated on the main thread. All code was pushed.
2023-07-13 | 11:00 | 14:00 | 3 h | Continued to research ways to improve performance of querying
2023-07-17 | 10:30 | 13:00 | 2.5 h | Started benchmarking where API limit was. Found out that 32x32 hits the minutely limit
2023-07-18 | 11:00 | 16:00 | 5 h | Conducted more research on ways to improve performance and discovered the ability to create an open session instead of reopening the connection for every call. This code was pushed.
2023-07-20 | 9:15 | 10:45 | 1.5 h | Group discussion
2023-07-20 | 11:00 | 15:00 | 4 h | Began researching ways to avoid limit, or at least exception handling
2023-07-22 | 16:00 | 20:00 | 4 h | Continued to research limit avoidance techniques. Pushed a change that disallowed the user from spamming query
2023-07-23 | 6:00 | 11:00 | 5 h | Implemented a 16x16 queue to avoid minutely limit reach with threaded timers, and added exception handling to catch such runtime errors. All code was pushed
2023-07-24 | 11:00 | 16:00 | 5 h | Pushed numerous bug fixes: such as the explicit stopping of timers if prematurely closed, and out of bounds error with 4x4 and 2x2 calls.
2023-07-25 | 18:00 | 0:00 | 4 h | Worked extensively on ways to improve rust code performance without full interpolation change. I tried putting rust code in separate thread, async rust function, cleaning up any redundant calculations, etc.
2023-07-26 | 12:00 | 20:30 | 8.5 h | Added lots of bug fixes, correct exception handling, and added new threads to distinguish between query and render time, with animated button text. All code was pushed.
2023-07-26 | 22:00 | 23:30 | 1.5 h | Additional bug fix was pushed in relation to render timer not being stopped after caught exception
2023-07-27 | 7:00 | 9:00 | 2 h | Worked on final presentation slides